## Use-case
| Feature | Use case | Individual | Family Member | Family Leader | Administrator | Use case description | Note
1 | Authentication | Register an account | TRUE | TRUE | TRUE | FALSE | Register for an account by providing required information, such as username, password, email, phone number, password
2 |  | Login to the system | TRUE | TRUE | TRUE | TRUE | Log in to the system by providing username or email and password or via Google login page
3 |  | Reset password | TRUE | TRUE | TRUE | TRUE | Reset the password in case the user forgets the password.
4 |  | Change password | TRUE | TRUE | TRUE | TRUE | Change account passwords for security reasons.
5 |  | Logout | TRUE | TRUE | TRUE | TRUE | Log out of the system.
6 |  | Remember login | TRUE | TRUE | TRUE | TRUE | Stay logged in to avoid having to enter login information every time you access the system.
7 | Account Management | View account list | FALSE | FALSE | FALSE | TRUE | Displays a list of all user's accounts
8 |  | Create new account | FALSE | FALSE | FALSE | TRUE | Administrator can create account for user without register
9 |  | Manage account's status | FALSE | FALSE | FALSE | TRUE | Administrator can ban/unban user's account
10 |  | Filter the account | FALSE | FALSE | FALSE | TRUE | Administrator can filter the account by username or email
11 | Profile Operation | View individual profile | TRUE | TRUE | TRUE | FALSE | View their profile within the system, allowing them to see and edit their personal information and settings.
12 |  | View profile of others | TRUE | TRUE | TRUE | FALSE | View profile of other user.
13 |  | Update individual profile | TRUE | TRUE | TRUE | FALSE | Change profile information.
14 |  | View friends list | TRUE | TRUE | TRUE | FALSE | View all of their friends list whom they are connected.
15 |  | View families list | FALSE | TRUE | TRUE | FALSE | Viw all of their family list.
16 | Calendar Opertation | View individual calendar | TRUE | TRUE | TRUE | FALSE | View individual user's events on calendar.
17 |  | View individual events on day | TRUE | TRUE | TRUE | FALSE | View events on specific days.
18 |  | Create individual event | TRUE | TRUE | TRUE | FALSE | Create individual event.
19 |  | Update individual event | TRUE | TRUE | TRUE | FALSE | Update individual event.
20 |  | Remove individual event | TRUE | TRUE | TRUE | FALSE | Remove event.
21 |  | Filter individual event on month | TRUE | TRUE | TRUE | FALSE | Filter their personal events occurring within a specific month on their calendar within the system.
22 |  | Filter all events on month | TRUE | TRUE | TRUE | FALSE | Filter all events, including both personal and family events, that occur within a specific month on their calendar within the system.
23 |  | View upcoming all events | TRUE | TRUE | TRUE | FALSE | View all upcoming event .
24 |  | View family calendar | FALSE | TRUE | TRUE | FALSE | View calendar in family group.
25 |  | View family events on day | FALSE | TRUE | TRUE | FALSE | View events on the specific days in the family calendar.
26 |  | Create family event | FALSE | FALSE | TRUE | FALSE | Create event in the calendar of the family group.
27 |  | Update family event | FALSE | FALSE | TRUE | FALSE | Update event in the calendar of the family group.
28 |  | Remove family event | FALSE | FALSE | TRUE | FALSE | Remove event in the calendar of the family group.
29 |  | Filter family events | FALSE | TRUE | TRUE | FALSE | Filter all event of the family group on a month.
30 |  | View upcoming family events | FALSE | TRUE | TRUE | FALSE | View all upcoming events in the family group.
31 |  | Add remind event | TRUE | TRUE | TRUE | FALSE | Add remind to the event.
32 |  | View remind on detail event | TRUE | TRUE | TRUE | FALSE | View all remind of event.
33 |  | Remind event on current day | TRUE | TRUE | TRUE | FALSE | Receive reminders of events.
34 |  | Delete remind event | TRUE | TRUE | TRUE | FALSE | Delete the remind of an event.
35 |  | Tag relative to event | TRUE | FALSE | FALSE | FALSE | Tag friends to the user's event.
36 | Conversation Management | Create two people's conversation | TRUE | TRUE | TRUE | FALSE | Create conversation with other user by sending the first message or connecting with the other user.
37 |  | View all two people's conversations | TRUE | TRUE | TRUE | FALSE | View the conversation with the other user.
38 |  | View two people's messages | TRUE | TRUE | TRUE | FALSE | View the messages with the other user.
39 |  | Send/Receive/Delete two people's messages | TRUE | TRUE | TRUE | FALSE | Send and receive messages from other people or they can delete their messages.
40 |  | Ban/Unban couple's conversation | TRUE | TRUE | TRUE | FALSE | Ban or unban the conversation between the two people.
41 |  | Create family conversation | TRUE | FALSE | TRUE | FALSE | Create conversation when they create new family.
42 |  | View all family conversations | FALSE | TRUE | TRUE | FALSE | View conversations they have participated in.
43 |  | View family's messages | FALSE | TRUE | TRUE | FALSE | View messages of the choosen family conversation.
44 |  | Send/Receive/Delete family messages | FALSE | TRUE | TRUE | FALSE | Send and receive messages from other people or they can delete their messages.
45 |  | Ban/Unban family conversation | FALSE | FALSE | TRUE | FALSE | Ban or undan the conversation of the family.
46 |  | Search conversation | TRUE | TRUE | TRUE | FALSE | Search all conversation by people's name or family's name.
47 | Relationship | Search relatives | TRUE | TRUE | TRUE | FALSE | Search for other individuals to identify potential family connections.
48 |  | Connect to relatives | TRUE | TRUE | TRUE | FALSE | Send requests for other individuals to identify potential family connections.
49 |  | Cancel connect to relatives | TRUE | TRUE | TRUE | FALSE | Remove existing connections.
50 | Family Operation | Create family | TRUE | TRUE | TRUE | FALSE | Create a new family on the platform.
51 |  | View family list | FALSE | TRUE | TRUE | FALSE | View a listing of all family they are part of.
52 |  | Merge family events to family members' calendar | FALSE | FALSE | FALSE | FALSE | Merge the event list of the family into the member's event list.
53 |  | View family home | FALSE | TRUE | TRUE | FALSE | Access a family's home page to see posts, calendar,... of all members of the family.
54 |  | Out family | FALSE | TRUE | FALSE | FALSE | Leave a family they are currently part of.
55 |  | View member list | FALSE | TRUE | TRUE | FALSE | View list of family members, family leader and total of members.
56 | Family Management | Authority leader role | FALSE | FALSE | TRUE | FALSE | Family leader can choose others family members to have family leader role if account is banned or deactive.
57 |  | Update member roles | FALSE | FALSE | TRUE | FALSE | Update leader roles to selected family members.
58 |  | Remove family members | FALSE | FALSE | TRUE | FALSE | Remove members from the family.
59 |  | Edit family's profile | FALSE | FALSE | TRUE | FALSE | Individual can view other profiles from post pages or profile page
60 |  | Remove family | FALSE | FALSE | TRUE | FALSE | Family leaders can disband the family.
61 |  | Add family member | FALSE | FALSE | TRUE | FALSE | Family leaders can add new members into the family.
62 | Post Operation | View individual posts in profile | TRUE | TRUE | TRUE | FALSE | View the
63 |  | View posts in news page | TRUE | TRUE | TRUE | FALSE | View the public posts of other people or your posts on the news page.
64 |  | View posts in family page | FALSE | TRUE | TRUE | FALSE | View the posts of the members of your family or your posts inside the family on the family page.
65 |  | Create new post in profile/news page | TRUE | TRUE | TRUE | FALSE | Post a new post in the profile and news page.
66 |  | Create new post in family page | FALSE | TRUE | TRUE | FALSE | Post a new post inside the family page.
67 |  | Update post in profile/news page | TRUE | TRUE | TRUE | FALSE | Update your post in the profile and news page.
68 |  | Delete posted post in profile/news page | TRUE | TRUE | TRUE | FALSE | Delete your post in the profile and news page.
69 |  | Update post in family page | FALSE | TRUE | TRUE | FALSE | Update your post in the family page.
70 |  | Delete posted post in family page | FALSE | TRUE | TRUE | FALSE | Delete your post in the family page.
71 |  | React in post | TRUE | TRUE | TRUE | FALSE | React a post such as Like,...
72 |  | View comment list | TRUE | TRUE | TRUE | FALSE | View the comment list of a post.
73 |  | Comment in post | TRUE | TRUE | TRUE | FALSE | Comment about a post.
74 |  | Update comment | TRUE | TRUE | TRUE | FALSE | Update your comment in a post.
75 |  | Delete comment | TRUE | TRUE | TRUE | FALSE | Delete your comment in a post.
76 |  | Edit audience | TRUE | FALSE | FALSE | FALSE | Individual can edit audience of their post (public or private)
77 |  | Tag relative to post | TRUE | FALSE | FALSE | FALSE | Individual can tag connected people to their post
78 |  | Save a post as an event | TRUE | TRUE | TRUE | FALSE | Individual, family member can choose a post an save this as an event in individual calendar
79 | Post Management | View post of user | FALSE | FALSE | FALSE | TRUE | View the post list of a user.
80 |  | Remove post of user | FALSE | FALSE | FALSE | TRUE | Remove a post of a user.
81 |  | Ban create post | FALSE | FALSE | FALSE | TRUE | Ban a user to post a new post.
82 | Family Tree Operation | Create new tree root | TRUE | FALSE | TRUE | FALSE | Allows individuals and family leaders to initiate the construction of their family tree by creating a new root node. The root could represent themselves or an ancestral figure from whom the family branches out. | ( individual with individual family tree and family leader with family tree of a family)
83 |  | View family tree for individual | TRUE | TRUE | TRUE | FALSE | Individuals, family members and family leaders are provided with tools to visually map out and display their personal family tree. This visual representation helps them to easily understand family connections, view generational links, and explore their lineage through an intuitive graphical interface.
84 |  | View joint family tree for family | FALSE | TRUE | TRUE | FALSE | Family members and family leaders are provided with tools to visually map out and display the family tree of their family.
85 |  | Add node in the tree | TRUE | FALSE | TRUE | FALSE | Enable individuals and family leaders to expand their family tree by adding new family members.
86 |  | Update node in the tree | TRUE | FALSE | TRUE | FALSE | Allow individuals and family leaders to update the information of a node in the family tree.
87 |  | Delete node in the tree | TRUE | FALSE | TRUE | FALSE | Permit individuals and family leaders to remove a family member from the tree
88 |  | Show all connected people | TRUE | FALSE | TRUE | FALSE | Allow individuals and family leaders to view all connected people that can be used to edit in the tree such as add, update and graft.
89 |  | Identify node in the tree | TRUE | FALSE | TRUE | FALSE | Allow individuals and family leaders to identify the node of the tree by linking another user profile to the node
90 |  | Add your own node | TRUE | FALSE | TRUE | FALSE | Allow individuals and family leaders to add a node that represents yourself into the tree by highlighting this node.
91 |  | Graft tree | TRUE | FALSE | TRUE | FALSE | Allow individuals and family leaders to graft the family tree of the other person or graft the personal family tree into the family tree of a family
92 |  | Show information of each node | TRUE | TRUE | TRUE | FALSE | Allow individuals, family members and family leaders to show more information about the node that has been chosen
93 | System Notification Operation | View connection request | TRUE | TRUE | TRUE | FALSE | View connection requests sent from relatives in notification to be able to accept or decline the request.
94 |  | Delete connection notification | TRUE | TRUE | TRUE | FALSE | Allow users to delete notifications after their connection requests are accepted.
95 |  | View tagged event by others | TRUE | TRUE | TRUE | FALSE | Receive and view notifications for events they're tagged in by relatives.
96 |  | Update tagged event notification | TRUE | TRUE | TRUE | FALSE | Adjust description notification details for users when event titles they're tagged in are changed.
97 |  | Receive updated tag notification | TRUE | TRUE | TRUE | FALSE | Be notified when there are changes to the attendee list of events they are tagged in, such as being added or removed tag by the event organizer.
98 |  | Delete tagged event notification | TRUE | TRUE | TRUE | FALSE | Remove notifications for events they're tagged in by relatives.

## Project
Total Project Tracking
# | Feature | Screen/Function | Screen/Function Description | In Charge | post | Actual | Updated | Update Details | Updated | Update Details
1 | Common | Home page | View home page when login successful | MinhNQ | done | ite1 | ite3 | Popup to confirm log-out | #
2 | Authentication | Account register | Register a new account | TungTQ | done | ite1 | # |  | #
3 |  | User login | Login by username (email) & password Login with Google | TungTQ | done | ite1 | ite3 |  | #
4 |  | Password reset | Reset password via email | TungTQ | done | ite3 | # |  | #
5 |  | Password change | Allow user to change password | TungTQ | done | ite3 | # |  | #
6 | Account Management | Admin dashboard | Admin can show the screen of accounts list | TungTQ | done | ite2 | ite3 |  | #
7 |  | Account lists | View and search all accounts | TungTQ | done | ite2 | # |  | #
8 |  | Add new account | Admin can add new account to the system | TungTQ | done | ite2 | # |  | #
9 |  | Account setting | Admin can view, change post (active/ban) and change role in detail account | TungTQ | done | ite2 | # |  | #
10 | Profile Operation | User profile | View the profile of user, view the list of friends, and list of joined families | MinhNQ | done | ite1 | ite3 | List of joined families | #
11 |  | Profile of other user | View the profile of other user | MinhNQ | done | ite3 | # |  | #
12 |  | Profile update | Update profile of user | MinhNQ | done | ite1 | ite2 | Change UI | #
13 | Calendar Operation | Individual calendar screen | User can view calendar (Lunar calendar, Gregorian calendar) and all events on calendar | PhongPH | done | ite1 | ite2 | View merged event | #
14 |  | Add new individual event | Add new individual event | PhongPH | done | ite1 | ite3 | Add template | #
15 |  | Events on a particular day of individual | View, edit and delete created individual events and view merged events when choose a particular day | PhongPH | done | ite1 | # | Popup delete, show process | #
16 |  | Filter individual events list by month | View, search individual events list each month View events detail on a day | PhongPH | done | ite2 | # |  | #
17 |  | Filter all events list by month | View, search individual and merged events list each month View events detail on a day | PhongPH | done | ite2 | # |  | #
18 |  | Upcoming events of individual | View individual and merged upcoming events | PhongPH | done | ite1 | # |  | #
19 |  | Reminded event list | View a list of created reminder events and events for the current day | PhongPH | done | ite2 | # |  | #
20 |  | Event reminder | View, add, edit, delete remind on detail event | PhongPH | done | ite3 | # |  | #
21 |  | Tag others in an event detail | View, add, delete tag others in an event detail | PhongPH | done | ite3 | # |  | #
22 |  | Family calendar screen | Family leader and family member view calendar (Lunar calendar, Gregorian calendar) and events on calendar | PhongPH | done | ite1 | # |  | #
23 |  | Add new family event | Family leader add family events | PhongPH | done | ite1 | # |  | #
24 |  | Family events on particular day | View created family events when choosing a particular day Family leader can edit, delete family events | PhongPH | done | ite2 | # |  | #
25 |  | Filter family events list | View and search family events by month on family page | PhongPH | done | ite2 | # |  | #
26 |  | Upcoming family events | View upcoming family events | PhongPH | done | ite2 | # |  | #
27 | Conversation Operation | Search conversation | Allow user to search conversations by username or family name | MinhNQ | done | ite2 | # |  | #
28 |  | Add new conversation of two people | Auto - create new conversation after connecting with an account Chat with account that has not already connected | MinhNQ | done | ite2 | # |  | #
29 |  | Add new family conversation | Auto - create new family conversation after creating a family | MinhNQ | done | ite2 | # |  | #
30 |  | Conversations list | View all conversations of two people and family conversations | MinhNQ | done | ite2 | # |  | #
31 |  | Box chat for two people | - View messasges of two people - Send, receive, delete messages - Ban, unban conversation - Allows users connected to the same conversation to receive messages immediately - Security method that keeps your messages secure | MinhNQ | done | ite2 | ite3 | WebSocket realtime Encrypt/decrypt messages | #
32 |  | Box chat for family | View messasges of family members Send, receive, delete messages Ban, unban conversation | MinhNQ | done | ite2 | # |  | #
33 | Relationship | Relative connection | - Allow user search unconnected relatives by phone number and connected relatives by name and phone number - Send connection request to searched relatives or disconnect relatives | KhangNS | done | ite1 | ite2 | Update search by phonenumber | ite3 | Update send connection requests to relatives, cancel requests, and accept or reject incoming requests from relatives
34 | Family Operation | Add new family home page | Allow user create new family with their family members by chosen number of number of generations in the family tree | KhangNS | done | ite1 | ite3 | Auto add by generation | #
35 |  | Family list | View list of family and access details of a family | KhangNS | done | ite2 | # |  | #
36 |  | Family home page | - View home page and post of all members of the family - Family members can out family - View list of family members, family leader, and total of family members | KhangNS | done | ite1 | ite2 |  | #
37 | Family Management | Family details | Allows family leader can edit family details Remove family | MinhNQ | done | ite1 | # |  | #
38 |  | Add new family member | Search known individuals and add member to join the family | KhangNS | done | ite2 | # |  | #
39 |  | Update family member | Remove family members Update family leaders role for family members | KhangNS | done | ite2 | # |  | #
40 |  | Remove family | Family leaders can remove a family page
41 | Post Operation | Post list on profile page | View, and delete individual post | HiepCD | done | ite1 | # |  | #
42 |  | Post list on news page | View post of connected relatives, family members and delete individual post | HiepCD | done | ite1 | ite2 | Family members | #
43 |  | Post list on family page | View, and delete post of family members | HiepCD | done | ite2 | # |  | #
44 |  | Add new post on profile/ news page | Allow user add new post in profile or news page | HiepCD | done | ite1 | # |  | #
45 |  | Add new post on family page | Allow family member add new post | HiepCD | done | ite2 | # |  | #
46 |  | Update post | Update posted post on profile, news or family page | HiepCD | done | ite2 | # |  | #
47 |  | Reaction in a post | Like each post, view total reaction each post | HiepCD | done | ite2 | # |  | #
48 |  | Comment in post | View comment detail and total comment in each post Add new comment and delete comment | HiepCD | done | ite2 | # |  | #
49 |  | Update comment | Edit uploaded comment details in post | HiepCD | done | ite2 | # |  | #
50 |  | Audience setting of post | Allow users choose mode of post (public, private) in their post | HiepCD | done | ite2 | # |  | #
51 |  | Save a post as an event | Convert information post to events and save in individual calendar | HiepCD | done | ite3 | # |  | #
52 | Post Management | post of individual user list | Allow manager view and remove post of user in system | HiepCD | to do | ite3 | # |  | #
53 |  | Ban individual posted post | Allow manager ban post of user in system | HiepCD | to do | ite3 | # |  | #
54 | Family Tree Operation | Family tree screen for individual | Create and view new family tree for individual | DucTD | done | ite1 | ite3 |  | #
55 |  | Family tree screen for family | View family tree for family page | DucTD | done | ite2 | ite3 |  | #
56 |  | Update family tree details | Allow individual or family leader update, delete information in family tree | DucTD | done | ite1 | ite3 |  | #
57 |  | Add new node in tree | Allow users to expand their family tree - Add by manual typing - Add by adding new family members by search user and get information of this user | DucTD | done | ite2 | ite3 |  | #
58 |  | Identify node in the family tree | Allow user to identify the node of the tree by linking another user to the node | DucTD | done | ite2 | ite3 |  | #
59 |  | Personal node | Auto highlight the node that represent yourself | DucTD | done | ite3 | # |  | #
60 |  | Graft tree of two connected people or person to family | Allow users to graft the family tree of the other person or graft the person into the family tree of a family | DucTD | done | ite3 | # |  | #
61 | System Notification Operation | View connection request of others | - Allow users to view notifications. - Allow users to accept or reject connection requests from relatives in notification . | KhangNS | done | ite3 | # |  | #
62 |  | Remove notification of connection request | - Allow users to delete notifications when a relative accepts a connection request. | KhangNS | done | ite3 | # |  | #
63 |  | View notifications of events tagged by other relatives. | - Allow users to view and delete notifications when they are tagged in an event and get reminders for that event. | KhangNS | done | ite3 | # |  | #
64 |  | Receive new notifications of tagged events when were edited about tagged relatives | - Auto-update reminder notification descriptions when the event title is changed by the owner. | KhangNS | done | ite3 | # |  | #
65 |  | Edit event notifications | - When users delete an event that tags others or untags others, they won't receive reminder of the event - When the user updates people that are tagged on the event, who are not untagged receive a notification of this change | KhangNS | done | ite3 | # |  | #
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150

## Iter 1
Iteration Tracking - Iteration 1
# | Feature | Screen / Function | Screen/Function Description | In Charge | post | SRS | Notes
1 | Common | Home page | View home page when login successful | MinhNQ | done
2 | Authentication | Account register | Register a new account | TungTQ | done
3 |  | User login | Login by username (email) & password Login with Google | TungTQ | done
4 | Profile Operation | User profile | View the profile of user, view the list friends, list family | MinhNQ | done
5 |  | Profile update | Update profile of user | MinhNQ | done
6 | Calendar Operation | Individual calendar screen | User can view calendar (Lunar calendar, Gregorian calendar) and all events on calendar | PhongPH | done
7 |  | Add new individual event | Add new individual event | PhongPH | done
8 |  | Events on a particular day of individual | View, edit and delete created individual events and view merged events when choose a particular day | PhongPH | done |  | update using Ajax
9 |  | Upcoming events of individual | View individual and merged upcoming events | PhongPH | done
10 |  | Family calendar screen | Family leader and family member view calendar (Lunar calendar, Gregorian calendar) and events on calendar | PhongPH | done
11 |  | Add new family event | Family leader add family events | PhongPH | done
12 | Relationship | Relative connection | - Allow user search unconnected relatives and connected relatives by name | KhangNS | done | II. 6.1
14 | Family Operation | Create family | Allow user create new family with their family members by add connected relatives | KhangNS | done | II. 7.1 | Change: Allow user create new family with their family members by chosen number of number of generations in the family tree
15 |  | Family home page | - View home page - Family members can out family | KhangNS | done
16 | Family Management | Family details | Allows family leader can edit family details Remove family | MinhNQ | done
17 | Post Operation | post list on profile page | View, and delete individual post | HiepCD | done |  | Popup and lack "back" button
18 |  | post list on news page | View post of connected relatives, family members and delete individual post | HiepCD | done
19 |  | Add new post on profile/ news page | Allow user add new post in profile or news page | HiepCD | done
20 |  | Update post | Update posted post on profile, news or family page | HiepCD | done
21 | Family Tree Operation | Family tree screen for individual | Create and view new family tree for individual | DucTD | done
22 |  | Edit family tree details | Allow add by manual typing, update, delete information in family tree | DucTD | done

## Iter 2
Iteration Tracking - Iteration 2
# | Feature | Screen / Function | Screen/Function Description | In Charge | post | SRS | Notes
1 | Account Management | Add new account | Allow admin to quickly create accounts for user | TungTQ | done
2 |  | Account lists | View and search all accounts | TungTQ | done
3 |  | Add new account | Admin can add new account to the system | TungTQ | done
4 |  | Account setting | Admin can view, change post (active/ban) and change role in detail account | PhongPH | done
5 | Celendar Opertation | Filter all events list by month | - View, search individual and merged events list each month - View individual event details on a day | PhongPH | done
6 |  | Family events on particular day | - View created family events when choose a particular day by family members - Edit, delete family events by family leader | PhongPH | done
7 |  | Filter family events list | View and search family events by month on family page | PhongPH | done
8 |  | Upcoming family events | View upcoming family events for family members | PhongPH | done
9 |  | Reminded event list | View the list of created reminder events and events of the day | PhongPH | done
10 | Conversation Operation | Conversations list | View all conversations of two people and family conversations | MinhNQ | done
11 |  | Search conversation | Allow user to search conversations by username or family name | MinhNQ | done
12 |  | Add new family conversation | Auto - create new family conversation after creating a family | MinhNQ | done
13 |  | Add new conversation of two people | Auto - create new conversation after connecting with an account Chat with account that has not already connected | MinhNQ | done | II. 5.1
14 |  | Box chat for two people | Allow user send/receive/delete messages with other user Ban/unban conversation | MinhNQ | done
15 |  | Box chat for family | Allow user send/receive/delete messages between family members Ban/unban conversation | MinhNQ | done | II. 5.4
16 | Family Operation | Family home page | View list of family members, family leader and total of family members | KhangNS | done
17 |  | Family list | Allow family leaders , family members to view list of family and access detail of a family | KhangNS | done | II. 7.2
18 | Family Management | Update family member | Remove family members Update family leaders role for family members | KhangNS | done
19 |  | Add new family member | Search known individuals and add member to join the family | KhangNS | done | II. 7.3
20 | Relationship | Relative connection | Allow user search unconnected relatives by phone number and connected relatives by name and phone number | KhangNS | done | II. 6.1 | Update
21 | Post Operation | post list on family page | Allow family members view post of other member and delete their posted post | HiepCD | done
22 |  | New post on family page | Create new post on family page | HiepCD | done |  | - Add "upload image" function in post at profile, news,family page
23 |  | Edit post on family page | Allow family members edit their posted post | HiepCD | done
24 |  | Reaction in post | Like each post, view total reaction each post | HiepCD | done
25 |  | Comment in post | - View comment detail and total comment in each post - Add new comment and delete comment | HiepCD | done
26 |  | Edit comment | Edit uploaded comment in post | HiepCD | done
27 |  | Audience setting of post | Edit view mode (private, public) of post | HiepCD | done
28 | Family Tree Operation | Identify node in the family tree | Allow user to identify the node of the tree by linking another user to the node | DucTD | done
29 |  | Family tree screen for family page | View screen contains family tree of a family | DucTD | done
30 |  | Add new family member in tree (by search user) | Allow users to expand their family tree by adding new family members by search user and get information of this user | DucTD | done

## Iter 3
Iteration Tracking - Iteration 3
# | Feature | Screen / Function | Screen/Function Description | In Charge | post | SRS | Notes
1 | Authentication | Password Reset | Send code to email, verify, reset password | TungTQ | done
2 |  | Password Change | Change password user's account | TungTQ | done
3 |  | Login by Google | Allow user login by google | TungTQ | done
4 | Calendar | Event reminder | View, add, delete remind event in detail event | PhongPH | done
5 |  | Tag connected relatives in an event detail | View, add, update, delete member in detail event | PhongPH | done
6 | Conversation Operation | Send/Receive/Delete messages of family (Updated) | Allows users connected to the same conversation to receive messages immediately | MinhNQ | done |  | Use Web Socket
8 | Profile Operation | Profile of other user | View the profile of other user | MinhNQ | done
9 | Post Operation | Tag connected relatives to the post | User can tag connected relative to post post | HiepCD | done |  | Change information design of staus
10 |  | Convert a post to an individual event | Convert information post to events and save in individual calendar | HiepCD | done |  | Update to modal form to edit
11 |  | post list on news page (update) | - Auto load new post according to scroll screen - Can change image when edit post | HiepCD | done
12 | Family tree | Infomation of a node | Allow users to see more infomation about the node and the link to your connected people profile if this node was linked | DucTD | done
13 |  | Personal node | Auto highlight the node that represent yourself | DucTD | done
15 |  | Graft tree of two connected people or person to family | Allow users to graft the family tree of the other person or graft the person into the family tree of a family | DucTD | done
16 | Relationship | Relative connection (update) | - Allow users to send connection requests to relatives, cancel requests. - Allow users to accept or reject incoming requests from relatives. | KhangNS | done | II. 6.1
17 | System Notification Operation | Connection request notification | - Allow users to view notifications when an unconnected sends a connection request and after request is accepted. - Allow users to accept or reject connection requests in the notification. - Allow users to delete notifications when a relative accepts a connection request. | KhangNS | done | II. 10.1
18 |  | Event notification | -Allow users to view notifications when they are tagged in an event and get reminders for that event. - Auto-update reminder notification titles when the event title is changed by the owner. - When users delete an event that tags others or untags others, they won't receive reminder of the event - When the user updates people that are tagged on the event, who are not untagged receive a notification of this change - Allow users to delete notifications when they are tagged in an event and get reminders for that event. | KhangNS | done