## Issue Report
Title | Description | Issue ID | State | Assignee | Created At | Due Date | Milestone | Functions/Screens
User login | User can login with the same username | 1 | Closed | TungTQ | 2024-01-11 | 2024-01-12 | Iter1 | User login screen
User register | User can register with the same username and phone number | 2 | Closed | TungTQ | 2024-01-11 | 2024-01-12 | Iter1 | User register Screen
User register | User can register without confirming wrong password | 3 | Closed | TungTQ | 2024-01-11 | 2024-01-12 | Iter1 | User register Screen
Security | Get session from account instead of user | 4 | Closed | PhongPH | 2024-01-13 | 2024-01-14 | Iter1 | Home screen
Calendar responsive | The bottom of calender extends quite a bit | 5 | Open | PhongPH | 2024-01-13 |  | Iter2 | Home screen
Search friend | Search for people not in the list but display all people in the list | 6 | Closed | KhangNS | 2024-01-14 | 2024-01-15 | Iter1 | Search bar
Unfriend | User1 deletes their friend, but the other users are deleted as well | 7 | Closed | KhangNS | 2024-01-16 | 2024-01-17 | Iter1 | Search Screen
Add friend | Users can add themselves and after add friend not still stay in this page | 8 | Closed | KhangNS | 2024-01-16 | 2024-01-17 | Iter1 | Search bar
Create group | Can't create group because of css's error | 9 | Closed | KhangNS | 2024-01-16 | 2024-01-17 | Iter1 | Search Screen
Not authorization in the group | Users and admins have the same role in the group | 10 | Closed | KhangNS | 2024-01-16 | 2024-01-17 | Iter1 | Group Screen
Update infomation group | Admin of group can't update them group's infomation | 11 | Open | MinhNQ | 2024-01-17 | 2024-01-24 | Iter1 | Group Screen
Delete group | Admin of group can't delete them group | 12 | Closed | MinhNQ | 2024-01-17 | 2024-01-24 | Iter1 | Group Screen
Out of group | User can't out of group | 13 | Closed | KhangNS | 2024-01-17 | 2024-01-24 | Iter1 | Group Screen
Create status | Status has not been created for individuals yet | 14 | Closed | HiepCD | 2024-01-18 | 2024-01-19 | Iter1 | Status screen
Sort status | Haven't sorted newest status first | 15 | Open | HiepCD | 2024-01-18 | 2024-01-30 | Iter1 | Status screen
Upload image in status | User uploads the user's image but status can't show this image | 16 | Open | HiepCD | 2024-01-18 | 2024-01-30 | Iter1 | Status screen
Status Screen | Remake status screen css | 17 | Closed | MinhNQ | 2024-01-19 | 2024-01-24 | Iter1 | Status screen
Profile | Users cannot upload photos to change their avatar | 18 | Open | MinhNQ | 2024-01-19 | 2024-01-20 | Iter1 | Profile screen
Create group in profile | After user click user's profile, they can not create group (do not show pop-up) | 19 | Open | MinhNQ | 2024-01-21 | 2024-01-22 | Iter1 | Profile screen
List friend in profile | Added friends are not displayed in the friend list | 20 | Closed | MinhNQ | 2024-01-21 | 2024-01-22 | Iter1 | Profile screen
Upload status | Other user can not view status of user's friend | 21 | Open | HiepCD | 2024-01-21 | 2024-01-30 | Iter1 | Status screen
Screen overflow error | Fill in the description for a post that is too long and will overflow the screen | 22 | Open | PhongPH | 2024-01-22 | 2024-01-30 | Iter1 | Status screen
Incorrect access authorization | Allows users unlimited access to the group. | 23 | Closed | KhangNS | 2024-01-22 | 2024-02-02 | Iter2 | Group Screen
View image invalid | Status without Image after choose editing and do not upload image still show default image | 24 | Closed | HiepCD | 2024-02-13 | 2024-03-15 | Iter2 | Status screen
25
Edit audience when create new status | When creating status user can't edit audience | 26 | Open | HiepCD | 2024-03-01 |  | Iter2 | Status screen
Delete image when edit status | When editting status user can't delete posted image | 27 | Open | HiepCD | 2024-03-02 |  | Iter2 | Status screen
Limit comment size | User can't send a comment with too large size | 28 | Open | HiepCD | 2024-03-03 |  | Iter2 | Status screen
Query to load status on news page | Consider to optimize complexity of the query | 29 | Open | HiepCD | 2024-03-04 |  | Iter3 | Status screen
30
31
32
33
34